## Backlog
Practicum 1
Work date | Work day | Ideal tasks remaining | Actual tasks remaining | Time spent Jochem | Completed tasks Jochem | Time spent Kiran | Completed tasks Kiran | Total tasks completed | Total time spent | Work date | Tasks worked on
2020-02-26 | 0 | 28 | 28 | 0 | 0 | 0 | 0 |  |  |  | Kiran | Jochem
2020-02-27 | 1 | 26.1333 | 25.3 | 6.5 | 1.35 | 6.5 | 1.35 | 2.7 | 13 | 2020-02-27 | 1, 2, 3 | 1, 2, 3
2020-02-28 | 2 | 24.2667 | 19 | 3.5 | 3.7 | 3 | 2.6 | 6.3 | 6.5 | 2020-02-28 | 7, 8, 9, 3 | 5, 6, 3, 10
2020-02-29 | 3 | 22.4 | 12 | 3.5 | 3 | 4 | 4 | 7 | 7.5 | 2020-02-29 | 11, 12, 13, 14 | 4, 15, 16
2020-03-01 | 4 | 20.5333 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-03-01 | - | -
2020-03-02 | 5 | 18.6667 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-03-02 | - | -
2020-03-03 | 6 | 16.8 | 5 | 5 | 4 | 5 | 3 | 7 | 10 | 2020-03-03 | 20, 21, 23 | 20, 21, 22, 23
2020-03-04 | 7 | 14.9333 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-03-04 | - | -
2020-03-05 | 8 | 13.0667 | 2 | 3 | 1 | 1 | 2 | 3 | 4 | 2020-03-05 | 24, 26 | 25
2020-03-06 | 9 | 11.2 | 1.8572 | 3 | 0.14285 | 0 | 0 | 0.14285 | 3 | 2020-03-06 | - | 27
2020-03-07 | 10 | 9.3333 | 1.6905 | 1 | 0 | 3 | 0.1667 | 0.1667 | 4 | 2020-03-07 | 27 | -
2020-03-08 | 11 | 7.4667 | 1.3809 | 1.5 | 0.14285 | 2.5 | 0.1667 | 0.30955 | 4 | 2020-03-08 | 27 | 27, 28
2020-03-09 | 12 | 5.6 | 1.0714 | 2 | 0.14285 | 2 | 0.1667 | 0.30955 | 4 | 2020-03-09 | 27 | 27, 28
2020-03-10 | 13 | 3.7333 | 0.7618 | 3 | 0.14285 | 2 | 0.1667 | 0.30955 | 5 | 2020-03-10 | 27 | 28, 19
2020-03-11 | 14 | 1.8667 | 0.45225 | 2 | 0.14285 | 2 | 0.1667 | 0.30955 | 4 | 2020-03-11 | 27, 19 | 28, 19
2020-03-12 | 15 | 0 | 0.1427 | 4 | 0.14285 | 4 | 0.1667 | 0.30955 | 8 | 2020-03-12 | 27, 19 | 28, 19
2020-03-13 | 15 | 0 | 0.1427 | 0 | 0 | 0 | 0 | 0 | 0
2020-03-14 | 15 | 0 | -0.00015 | 2 | 0.14285 | 0 | 0 | 0.14285 | 2

## Tasks
Task Nummer | Title | Estimate | status | Owner
1 | Make UML Design | 2 | 100% | JL,KS
2 | Make Structure | 4 | 100% | JL,KS
3 | Logic for classes practica 1 | 10 | 100% | JL,KS
4 | AI | 5 | 100% | JL
5 | schuin move | 2 | 100% | JL
6 | pawn kil | 2 | 100% | JL
7 | print color pawns | 2 | 100% | KS
8 | print input error | 0.5 | 100% | KS
9 | pawn wins when on other side | 0.5 | 100% | KS
10 | fix bug ~Board destructor | 1 | 100% | JL
11 | update UML | 1 | 100% | KS
12 | update Board class+ add moveStr | 0.75 | 100% | KS
13 | refined console output | 0.1 | 100% | KS
14 | print Chess logo on screen | 0.3 | 100% | KS
15 | fix bug AI take | 0.5 | 100% | JL
16 | fix bug pawn jump | 0.5 | 100% | JL
17 | created classes for the other Pieces on Board | 2 | 100% | KS
18 | Logic for classes practica 2 | 10 | 100 | JL,KS
19 | Checkmate functionality | 5 | 100% | JL
20 | Refactorization | 10 | 100% | JL,KS
21 | Seperate IO into it's own file | 2 | 100% | JL,KS
22 | noBlockers() function | 1.5 | 100% | JL
23 | Clear() function | 0.5 | 100% | JL,KS
24 | Implement inheritance | 4 | 100% | KS
25 | Squashed repetitve functions | 3 | 100% | JL
26 | make const functions | 1 | 100% | KS
27 | Refactorization boogaloo | 10 | 100% | JL,KS
28 | AI bugs | 10 | 100% | JL